## User Stories
Title | Link | Hours | Developer | Status | Team | Dep. Row | Dependency | Clarification/Comments | Status | Risks | Issues
5.3.2.1_6 Create Account_New Account_(C_&_I) |  | - |  |  | MX | [5 empty] | We couldnt find an estimate in hours or technical design. The user story doesnt appear in Sharepoint
Private Equity 3 | Sharepoint Link | 10 |  |  | MX | [5 empty] | The Technical design section is missing
R_AML_PEP_Confirmation | Sharepoint Link |  |  |  | MX | [5 empty] | The Technical design section AND ESTIMATED HOURS ARE missing
5.3.4.17_2 Maintain Account Data_liquidiert | Sharepoint Link | 30 | Antonio Mora | Analyzing | MX | [5 empty] | The description and technical design on this user story are confusing. Maybe a call to check this out or write down more details could help
5.3.4.2_1 Maintain Account_Create Task to maintain account data | Sharepoint Link | 10 | Gabriela Morales | Analyzing | MX |  |  | do we have to create account admin? Account admin is a lookup field to user or contact (in filed mapping appears both) Who are the task owners ?
5.3.5.0_0 Maintain Contact Data_Maintaining the external person data | Sharepoint Link | 60 | Carlos Desigaud | Analyzing | MX |  |  | The new component and lightning page will be in contacts or external person? Technical design mock to see flow would help
5.3.2.1_8 Create Account_Hide LCSP for unqualified Accounts | Sharepoint Link | 16 | Antonio Mora | Analyzing | MX |  |  | For group is this refering to the standard account teams? How are related the account teams, by contacts?
5.3.4.2_3 Maintain Account_Maintain Auditor | Sharepoint Link | 20 | Scarlet Coria | Analyzing | MX |  |  | Why use a lightning component and not a standard related list for the auditors objects?
[13 empty] | All | Done | In progress
[12 empty] | Totals | 146 | 0 | 0
[12 empty] | CZ | 0 | 0 | 0
[12 empty] | MX | 146 | 0 | 0