## User Stories
Title | Link | Hours | Developer | Status | Team | Dep. Row | Dependency | Clarification/Comments | Status | Risks | Issues
5.3.2.1_6 Create Account_New Account_(C_&_I) |  | - |  |  | MX | [5 empty] | We couldnt find an estimate in hours or technical design. The user story doesnt appear in Sharepoint
Private Equity 3 | Sharepoint Link | 10 |  |  | MX | [5 empty] | The Technical design section is missing
R_AML_PEP_Confirmation | Sharepoint Link |  |  |  | MX | [5 empty] | The Technical design section AND ESTIMATED HOURS ARE missing
5.3.4.17_2 Maintain Account Data_liquidiert | Sharepoint Link | 30 | Antonio Mora | Analyzing | MX | [5 empty] | The description and technical design on this user story are confusing. Maybe a call to check this out or write down more details could help
5.3.4.2_1 Maintain Account_Create Task to maintain account data | Sharepoint Link | 10 | Gabriela Morales | Analyzing | MX |  |  | do we have to create account admin? Account admin is a lookup field to user or contact (in filed mapping appears both) Who are the task owners ?
5.3.5.0_0 Maintain Contact Data_Maintaining the external person data | Sharepoint Link | 60 | Carlos Desigaud | Analyzing | MX |  |  | The new component and lightning page will be in contacts or external person? Technical design mock to see flow would help
5.3.2.1_8 Create Account_Hide LCSP for unqualified Accounts | Sharepoint Link | 16 | Antonio Mora | Analyzing | MX |  |  | For group is this refering to the standard account teams? How are related the account teams, by contacts?
5.3.4.2_3 Maintain Account_Maintain Auditor | Sharepoint Link | 20 | Scarlet Coria | Analyzing | MX |  |  | Why use a lightning component and not a standard related list for the auditors objects?
5.3.4.2_3 Maintain Account_Maintain Auditor |  |  | Scarlet Coria | Pending | MX |  |  | • Auditor field in account will not be used anymore? (DEAL_Auditor__c) • Is there any criteria to define an Auditor? • Is there a restriction on the number of auditors that you can add? Only Primary and secondary? • Could we have more details on how the primary or secondary auditor checkbox fields will work • Entity Auditor will only be editable in GUP and read only in subsidiaries? • Only a specific kind of user can create auditors? The link to the related user story is not working.
5.3.1.1_1 GDPR Compliance_Maintain data for Federal Data Protection Act |  |  | Scarlet Coria | Pending | MX |  |  | • What does double opt-in email means? • Do we need a workflow/process builder for this solution?
5.3.4.18_1 Maintain Account Data_Client Feedback Manager hinterlegen und diesen informieren |  |  | Scarlet Coria | Pending | MX |  |  | • What is the type for a Client Feedback Manager? Contact/User? • Defining the text for the email templates that informs the user when he/she is selected as CFM would be needed • How someone can be identified as CFM? Only by selecting the name from the lookup at the account? |  |  |  |  | All | Done | In progress
5.3.4.2_1 Maintain Account_Create Task to maintain account data |  |  | Gabriela Morales | Pending | MX |  |  | account admin is a look up field? |  |  |  | Totals | 146 | 0 | 0
Account is Individual Entity |  |  | Gabriela Morales | Pending | MX |  |  | What does individual (entity) mean? |  |  |  | MX | 146 | 0 | 0
R_Account_Data Management_Maintain Account - Concern Hierarchy |  |  | Gabriela Morales | Pending | MX |  |  | which account fields are goint to be in the dinamic report?
Data Management_ Contact_Reactivating billing recipients |  |  | Gabriela Morales | Pending | MX |  |  | How billing addreses of a contact are identified?
5.3.2.1_8 Create Account_Hide LCSP for unqualified Accounts |  |  | Antonio Mora | Pending | MX |  |  | For group is this refering to the standard account teams? When an account group is mentioned, what does it mean or how this works? Where should the informational message be displayed? Lcsp will be hidden when the record type is changed to unqualified or the related to group teams happens or when both conditions are met? When the account is unqualified and the LCSP value is hidden, the value will be removed or it will be shown again when the account is qualified again?
R_ Client Acceptance & Continuance - Data Quality (ACCOUNT Frame) |  |  | Antonio Mora | Pending | MX |  |  | Is CA&C a role, profile or user?
Dubletten Meldung |  |  | Carlos Desigaud | Pending | MX |  |  | For lightning component for duplicated records, can we use the existent duplicated record rules or should we create a new one with other criteria to this specific user story?
5.3.5.0_0 Maintain Contact Data_Maintaining the external person data |  |  | Carlos Desigaud | Pending | MX |  |  | Where should be displayed the first component? Which are the local fields and what it means with “hiding”? Where is going to be displayed and how will be the layout of the lightning page (mock)? Which fields are going to be updated by the trigger? What should happen if I need to update more than 100 records? About what field should be created the roll up summary?
• R_ 2.3.3.5_1 Sub-contracting with Third Party-Prepare and Execute Indpendence & Risk |  |  | Edwin Resendiz | Pending | MX |  |  | o The object called “Third Party Providers” is not in the Data mapping and the user story doesn’t said the type of the fields for this object:  Account name.  Country.  Relevant Parties.  Independence Information. o The button “start work flow”, will it be fired on the Lead, Opportunity, Engagement objects or in the new custom object called Third Party Providers? o What does ‘Is the Independence Information for any of the entities SEC (Value of Rulset) Restricted (Value of Desgination)?’ mean? o How to work the condition ‘Is any (other) Third Party Provider added (if Count(Third Party Provider) > 0)?’, is it a condition or question showed In the flow?
• .3.4.5_2 Maintain Account Data_VAT-ID Prüfung_Recherche |  |  | Edwin Resendiz | Pending | MX |  |  | hat is the ‘VID-ID’ and in which accounts will be available? o Is the country value in the address object or will be a fiel in opportunity? o We need more time in order to analyze the user story and have more comments.