## User Stories
Title | Hours | Developer | Status | Team | Dep. Row | Dependency | Clarification/Comments | Status | 2018-10-02 | 2018-10-03 | Risks | Issues
5.3.2.1_10_Create Account_create address | 40 | Sabina |  | CZ | 4 | 5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | Auto-filling the addresses from Google is not possible for custom fields. Empire Time integration out of scope for sprint 1. Misalignment between user story and fields list - started implementing as mentioned in the user story. | In Progress
5.3.2.3_1 Create Account_Define sector and industry | 30 | Jan |  | CZ | 29 | Data Management_Create Account_concern data | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification |  |  | Started by Jan, but eventually blocked by data model misalignment
5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | 40 | Carlos Desigaud y Mario Suarez(Shadow) | Work In Progress | MX | 16 | 5.3.2.1_6 Create Account_New Account | 1. Are dependant user stories already complete? 5.4.3.1_4 Status is completed?(Doesn’t appears in document) 5.3.8.13 Status is completed? (Doesn’t appears in document) 2. ¿How can we handle the 'Qualified accounts: LCSP, Konzern(Company)Account Admind, Account Admin)" part that appear on mandatory fields? Is it a field a record type, a picklist? R=Theyre fields 3. We need the Map Field to see which objects are available. For Example: Economically Authorized/PEP fieldRESPONDED 5. Button START WORKFLOW just calls the visual flow to capture required fields right? RESPONDED r= Yes 6. According to the Request for GwG, is a fact that the process will automatically send a task or email when a qualified account in workflow reaches the status Client Acceptance? Because the user story is not so clearly talking about that point (It says "perhaps"). | New | · Headquarter field related with 5.3.2.1_6 Create Account_New Account does not exist. · Label name should be “In use für split billing?” or “In use for Split Billing” · START EMPIRE TIME ----- Are these next two sentences refering to create validation rules for this field? o Must be later than 01.01.1990 o Before engagement start date (this field doesn´t exit) · The text "automatically created if account is set from qualified to unqualified (date of change)" for END EMPIRE TIME do this belongs to another user story? R=Put the today date with a workflow · Legal Entity is missing the field type in the mapping field · Are “Single Sales Revenue” and “Revenue” the same field? · Are “Balance Sheet Total” and “Balance Sum (balance sheet)” the same field? · Fiscal Year has a DateTime type in the excel and was created as Number type · Extract from commercial register is an upload field type. R=They're gonna be attachments · Economically authorised/PEP missing field type |  |  | Access to field mapping, Acces to Sharepoint
5.3.3.1_1 Create Contact_Enter available data_Contact | 20 | Jan |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | In Progress
5.3.3.1_4 Create Contact_Enter available data_Externe Person | 4 | Jan |  | CZ | 16 | 5.3.2.1_6 Create Account_New Account | Email sent out on 27/9 for small clarification. To be discussed with PO | Requires Clarification
5.3.3.2_1 Create Contact_System check, if data is existing (duplicate check) | 4 | Barbora |  | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact |  | In Progress
5.3.3.5 Create contact_connect a contact person to a biling address | 20 | Sabina |  | CZ | 2 | 5.3.2.1_10_Create Account_create address | There is a lot of text in German in the acceptance criteria. To be discussed with PO | Requires Clarification
5.3.4.1_2_Maintain Account Data -Define Sector and Industry | 40 | Jan |  | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
5.3.4.1_3 Maintain Account_Set Sector/Industry declination | 20 | Jan |  | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
5.3.4.8_1 Maintain Account Data_Notify about changes within German and Global Client Programs | 8 | Scarlet Coria | Work In Progress | MX |  |  | 1.-C&I Admin is a Role/Profile/Queue ? R=Profile 2.-The notification will be sent whenever one of the fields defined is modified on the parent account? R= 3.-Global and German Client Programs are record types? a single Field? 4.-Parent account is determined by the record type? (because of the structure) 5.-Do we need to put the templates in a specific folder? | New | 6.-The email templates mention <insert old record>, <insert new record> and <insert affected field>. The old values in a record can only be accessed by using a trigger. Solutions proposed: ---------SOLUTION 1------------------------------ a. Enable the History Tracking to the specified account fields and put it into the page layouts b. Send an email with the link of the account to see the modifications. -This solution will not include the old record, new record and affected field on the email template but on the record page itself. ***FIELDS THAT DOESN'T EXIST In Page Layout (Pending review to see if they exist in field mapping file)*** -Global LCSP - Category of Client Program Global and Client Program DE - Approval CIR - Stock exchange index - Auditor (Do we need to use any of the 3 following fields?) *Audit Previous FY Revenue *Audit Current FY Target *Lead Audit & Assurance Partner FIELDS WITH ISSUES - Account Number: Appears as Read only (Standard and custom) - Try for different record types - Account Name cannot be modified because of a validation rule previously defined. ---------SOLUTION 2------------------------------ -Generate an email template for every field -Generate a single workflow for every field -This solution can include the affected field and the new value of the affected field but not the old values. It also needs to be noted that it would require maintaining lot of workflows and templates |  |  | Access to field mapping, Acces to Sharepoint
5.3.5.0_1 Maintain Contact Data_Maintaining the external person data (optional) | 2 | Barbora |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New | [5 empty] | All | Done | In progress
5.3.7.7_1 Data Cleansing_Duplicates check (Contact) | 4 | Barbora |  | CZ |  |  |  | Done |  |  |  |  | Totals | 502 | 68 | 66
C&I_Tools_Manage Regions | 30 | Edwin Resendiz | Work In Progress | MX |  |  | • In the description says “Centrally edit and update regions and locations” making it seem like a bulk edit but later in the acceptance criteria it says it needs to be in the Account layout turning it into a single record requirement. Just to double check, it's needs to be a bulk or single record component? • In the section of the “Reporting”, Do I need to create the Reports or this values need to available in order to create a report? | New | • In SharePoint this user story has the wrong mock, it is for another user story (5.3.2.4_1 Create Account_Enter additional information on account qualifiziert). • The following fields were created by us but are missing in the field mapping file: o Region- Deal_Region__c. o Location- Deal_Location__c. o Regional Market Leader - Deal_Regional_Market_Leader__c. |  |  | • The user depends of the in progress : 5.3.2.1_10_Create Account_create address. • There is not access to Vision Image in order to check the design. • The permissions part for checkbox "Declination Location is not defined yet. | CZ | 351 | 68 | 64
5.3.2.1_1 Maintain Account_Duplicate Check Edit Process | 2 | Arquimidez Mora | Work In Progress | MX | 2 | 5.3.2.1_10_Create Account_create address |  | In Progress |  |  | Dependency in progress. Take into account that for the needed fields(Headquarter Country, ZIP Code, Street, City) they need to be different than formulas in order to be used in the duplicate rules cause HQ country already exists and is a formula field |  | MX | 151 | 0 | 2
5.3.2.1_6 Create Account_New Account | 4 | Jan |  | CZ |  |  |  | Done
5.3.2.1_6 Create Account_New Account_(mandatory) by searching in DEAL and Orbis | 35 | Sabina |  | CZ |  |  | We need the ORBIS managed package to proceed | On Hold
5.3.2.1_6 Create Account_New Account_Set Dunning block | 20 | Sabina |  | CZ |  |  |  | Done
5.3.3.2_2 Create External Person_System check, if data is existing (duplicate check) | 5 | Barbora |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New
5.3.X.X_XX Create Account_new account_generateAccountNumber | 2 | Barbora |  | CZ |  |  |  | Done
5.3.X.X_XX Create contact_new contact_generateContactNumber | 1 | Barbora |  | CZ |  |  |  | Done
5.3.X.X_XX Create external Person_new external person_generateExternalPersonNumber | 2 | Barbora |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | Done
C&I_Display German and Global Client Programs FY20 | 30 | Gabriela Morales Cuevas | Waiting for Status | MX | 29 | Data Management_Create Account_concern data | 1. The status of this user story is Canceled, is this status correct? 3. The fields mentioned in this user story in which record types of accounts should be visible? 4. These fields can be grouped in a section? | New |  |  | This user story is dependent with Data Management_Create Account_concern data but the status of this user story is “Requires Clarification”
C&I_Manage FG 500 | 5 | Adrian Olvera | Work In Progress | MX | 23 | C&I_Display German and Global Client Programs FY20 | From which page layouts needs to be added and in which needs to be removed (what is C&I data), all the security & visibility will be done on latest springs | New |  |  |  | Need field mapping file
C&I_Manage Mountainview client portfolio | 8 | Scarlet Coria | Work In Progress | MX | 23 | C&I_Display German and Global Client Programs FY20 | Doesn't specify component or if it exists | New |  |  | We don't know which component they are refering to and which other objects or components it affects. | Access to field mapping, Acces to Sharepoint
Classifiy by Deloitte Private | 20 | Antonio Mora y Rosario Lopez Calderon | Work In Progress | MX | 23 | C&I_Display German and Global Client Programs FY20 | 1.-In which object should the picklist called "Classification by Deloitte Private" should be created? 2.-Is "gCRM Global Ultimate Parent Layout" page layout the same as "ultimate parent account layout"? 3.-What is "the parent view lightning component"? 4.-Permissions and dependencies will be up to another sprint | New |  |  | Dependency in progress | Access to field mapping, Acces to Sharepoint
Client Category | 8 | Arquimidez | Work In Progress | MX | 23 | C&I_Display German and Global Client Programs FY20 |  | New |  | The field has been created and in layout. Waiting only for component clarification |  | Has a depedency in an unespecified and/or unexisting component. Involves pending permissions to be completed
Create Account_Setup Account Team | 4 | Barbora |  | CZ |  |  |  | Done
Data Management_Create Account_concern data | 10 | Barbora |  | CZ | 30 | Data Management_Create Account_GUP | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
Data Management_Create Account_GUP | 4 | Barbora |  | CZ |  |  |  | Done
Data Management_Set qualified account to unqualified account | 20 | Barbora |  | CZ | 4 | 5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | Option 1 for design. What does deactivating billing recipient mean? To be discussed with PO. | Requires Clarification
Global Search_Account | 0 | Barbora |  | CZ |  |  |  | Done
Global Search_Contact | 0 | Barbora |  | CZ |  |  |  | Done
Global Search_External Person | 1 | Barbora |  | CZ |  |  | The shortest option from the two was implemented | Done
Highlight Panel_1 | 1 | Barbora |  | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | Waiting for dependent class to be completed | New
Highlight Panel_2 | 1 | Barbora |  | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact | Waiting for dependent class to be completed | New
Highlight Panel_3 | 1 | Barbora |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New
Mobile External Person | 2 | Barbora |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | Done
Mobile_Account | 2 | Barbora |  | CZ |  |  |  | Done
Mobile_Contact | 2 | Barbora |  | CZ |  |  |  | Done
Create Contact_Setup contact Team | 20 | Barbora |  | CZ |  |  |  | Done
Data Management_Contact_Deletion Requirement External Person (DSGVO) | 30 | Sabina |  | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact | New record type for "locked" layout to be created - record should be updated with this record type when the deletion request checkbox is checked. | New