## User Stories
Title | Hours | Developer | Status | Link | Current Status Comments | Team | Dep. Row | Dependency | Clarification/Comments | Status | 2018-10-02 | 2018-10-03 | 2018-10-04 | Risks | Issues
5.3.2.1_10_Create Account_create address | 40 | Sabina |  |  |  | CZ | 4 | 5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | Auto-filling the addresses from Google is not possible for custom fields. Empire Time integration out of scope for sprint 1. Misalignment between user story and fields list - started implementing as mentioned in the user story. | In Progress
5.3.2.3_1 Create Account_Define sector and industry | 30 | Jan |  |  |  | CZ | 29 | Data Management_Create Account_concern data | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification |  |  |  | Started by Jan, but eventually blocked by data model misalignment
5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | 40 | Carlos Desigaud y Mario Suarez(Shadow) | Work In Progress | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=30&Source=https%3A%2F%2Fteams%2Ede%2Edeloitte%2Ecom%2Fsites%2FDeal%2FLists%2FUser%2520Stories%2FAllItems%2Easpx%23InplviewHash70ce21e7%2Dc6c7%2D4fcb%2D9b0d%2D69c10747ebfd%3D&ContentTypeId=0x0100B3FFFB2C5B67514A9A5256534188BC65 | Done • Mandatory and optional fields were created • Fields added in the Qualified account page layout • Quick action button added to account record page layout • Visual flow added in a lightning component called by a quick action button • Fields already added to the visual flow • Form in the visual flow displays the current account information • Form in the visual flow is now able to update the account information Pending • Validate some of the unpopulated fields • Add lookup to the user as LCSP • Validate Engagement Start Date • Workflow to send emails and tasks | MX | 16 | 5.3.2.1_6 Create Account_New Account | 6. According to the Request for GwG is not so clearly talking about that point (It says "perhaps"). Pendeing to know if that automated task belongs to this user story | New | START EMPIRE TIME ----- Are these next two sentences refering to create validation rules for this field? Pending to check for the engagement start date due to an account could have multiple engagements o Must be later than 01.01.1990 o Before engagement start date (this field doesn´t exit) R=Just in engagement, compare to account empire start date R=Send an email and a task por GwG · Legal Entity is missing the field type in the mapping field · Economically authorised/PEP missing field type |  |  | A design or mockup of the page layouts for the qualified and unqualified account is needed
5.3.3.1_1 Create Contact_Enter available data_Contact | 20 | Jan |  |  |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | In Progress
5.3.3.1_4 Create Contact_Enter available data_Externe Person | 4 | Jan |  |  |  | CZ | 16 | 5.3.2.1_6 Create Account_New Account | Email sent out on 27/9 for small clarification. To be discussed with PO | Requires Clarification
5.3.3.2_1 Create Contact_System check, if data is existing (duplicate check) | 4 | Barbora |  |  |  | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact |  | In Progress
5.3.3.5 Create contact_connect a contact person to a biling address | 20 | Sabina |  |  |  | CZ | 2 | 5.3.2.1_10_Create Account_create address | There is a lot of text in German in the acceptance criteria. To be discussed with PO | Requires Clarification
5.3.4.1_2_Maintain Account Data -Define Sector and Industry | 40 | Jan |  |  |  | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
5.3.4.1_3 Maintain Account_Set Sector/Industry declination | 20 | Jan |  |  |  | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
5.3.4.8_1 Maintain Account Data_Notify about changes within German and Global Client Programs | 8 | Scarlet Coria | Work In Progress | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=163&Source=https%3A%2F%2Fteams%2Ede%2Edeloitte%2Ecom%2Fsites%2FDeal%2FLists%2FUser%2520Stories%2FAllItems%2Easpx%23InplviewHash70ce21e7%2Dc6c7%2D4fcb%2D9b0d%2D69c10747ebfd%3D&ContentTypeId=0x0100B3FFFB2C5B67514A9A5256534188BC65 | Done: • Investigation of the usage of the function PRIORVALUE • Generation and testing of a new field to store the previous value of a modified field • Generation and testing of the field into a workflow, using two workflow actions: o Field update for the previous value o Email template • Generation of temporal fields, email templates and workflows for the priorvalues updates for 7 fields. Tasks to complete: • Custom labels in email template to allow for german translation • Pending change the priorvalue for picklist to actual text, cause currently it saves the API name which is a number • Generation of temporal fields, email templates and workflows for the priorvalues updates for 7 fields. | MX |  |  | 3.-Global and German Client Programs are record types? a single Field? 5.-Do we need to put the templates in a specific folder? | New
5.3.5.0_1 Maintain Contact Data_Maintaining the external person data (optional) | 2 | Barbora |  |  |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New | [6 empty] | All | Done | In progress
5.3.7.7_1 Data Cleansing_Duplicates check (Contact) | 4 | Barbora |  |  |  | CZ |  |  |  | Done | [5 empty] | Totals | 502 | 68 | 66
C&I_Tools_Manage Regions | 30 | Edwin Resendiz | Work In Progress | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=333&Source=https%3A%2F%2Fteams%2Ede%2Edeloitte%2Ecom%2Fsites%2FDeal%2FLists%2FUser%2520Stories%2FAllItems%2Easpx%23InplviewHash70ce21e7-c6c7-4fcb-9b0d-69c10747ebfd%3D&ContentTypeId=0x0100B3FFFB2C5B67514A9A5256534188BC65 | Points completed: • Fill the picklists according of the postal code inserted. • UI of Lightning component. • The current account is updated. • Messages of the success updated is displayed. • Allow to select location only when ‘Disable Location’ is checked Points in progress: • The validation of the users. • Fill the picklist when postal code is removed. | MX |  |  | • In the description says “Centrally edit and update regions and locations” making it seem like a bulk edit but later in the acceptance criteria it says it needs to be in the Account layout turning it into a single record requirement. Just to double check, it's needs to be a bulk or single record component? • In the section of the “Reporting”, Do I need to create the Reports or this fields just need to be available in order to create a report? | New | • In SharePoint this user story has the wrong mock, it is for another user story (5.3.2.4_1 Create Account_Enter additional information on account qualifiziert). • The following fields were created by us but are missing in the field mapping file: o Region- Deal_Region__c. o Location- Deal_Location__c. o Regional Market Leader - Deal_Regional_Market_Leader__c. | For the locations that have the Slash, for exapmple "Berlin / Erfurt / Magdeburg", they're going to be in a single picklist option or they're going to be presented as 3 picklist options to the user? |  |  | • There is not access to Vision Image in order to check the design. • The permissions part for checkbox "Declination Location" aregoing to be defined. | CZ | 351 | 68 | 64
5.3.2.1_1 Maintain Account_Duplicate Check Edit Process | 2 | Arquimidez Mora | Work In Progress | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=486&Source=https%3A%2F%2Fteams%2Ede%2Edeloitte%2Ecom%2Fsites%2FDeal%2FLists%2FUser%2520Stories%2FAllItems%2Easpx%23InplviewHash70ce21e7%2Dc6c7%2D4fcb%2D9b0d%2D69c10747ebfd%3D&ContentTypeId=0x0100B3FFFB2C5B67514A9A5256534188BC65 | Duplication and validation rules where created, but they're validating with the Shiping address instead of the HQ address | MX | 2 | 5.3.2.1_10_Create Account_create address |  | In Progress |  |  |  | Dependency in progress. Take into account that for the needed fields(Headquarter Country, ZIP Code, Street, City) they need to be different than formulas in order to be used in the duplicate rules cause HQ country already exists and is a formula field |  | MX | 151 | 0 | 2
5.3.2.1_6 Create Account_New Account | 4 | Jan |  |  |  | CZ |  |  |  | Done
5.3.2.1_6 Create Account_New Account_(mandatory) by searching in DEAL and Orbis | 35 | Sabina |  |  |  | CZ |  |  | We need the ORBIS managed package to proceed | On Hold
5.3.2.1_6 Create Account_New Account_Set Dunning block | 20 | Sabina |  |  |  | CZ |  |  |  | Done
5.3.3.2_2 Create External Person_System check, if data is existing (duplicate check) | 5 | Barbora |  |  |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New
5.3.X.X_XX Create Account_new account_generateAccountNumber | 2 | Barbora |  |  |  | CZ |  |  |  | Done
5.3.X.X_XX Create contact_new contact_generateContactNumber | 1 | Barbora |  |  |  | CZ |  |  |  | Done
5.3.X.X_XX Create external Person_new external person_generateExternalPersonNumber | 2 | Barbora |  |  |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | Done
C&I_Display German and Global Client Programs FY20 | 30 | Gabriela Morales Cuevas | Waiting for Status(On Hold) | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=464&Source=https%3A%2F%2Fteams%2Ede%2Edeloitte%2Ecom%2Fsites%2FDeal%2FLists%2FUser%2520Stories%2FAllItems%2Easpx%23InplviewHash70ce21e7%2Dc6c7%2D4fcb%2D9b0d%2D69c10747ebfd%3D&ContentTypeId=0x0100B3FFFB2C5B67514A9A5256534188BC65 | User story was clarified and we were searching for the wrong one. Currently working on the right one | MX | 29 | Data Management_Create Account_concern data |  | New |  |  |  | This user story is dependent with Data Management_Create Account_concern data but the status of this user story is “Requires Clarification”
C&I_Manage FG 500 | 5 | Adrian Olvera | Completed | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=627&Source=https%3A%2F%2Fteams%2Ede%2Edeloitte%2Ecom%2Fsites%2FDeal%2FLists%2FUser%2520Stories%2FAllItems%2Easpx%23InplviewHash70ce21e7-c6c7-4fcb-9b0d-69c10747ebfd%3D&ContentTypeId=0x0100B3FFFB2C5B67514A9A5256534188BC65 |  | MX | 23 | C&I_Display German and Global Client Programs FY20 | From which page layouts needs to be added and in which needs to be removed (what is C&I data), all the security & visibility will be done on later springs | New
C&I_Manage Mountainview client portfolio | 8 | Scarlet Coria | Work In Progress | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=583 | • Created Field • Class to identify parent account to use in component: DEAL_IsParentAccount() Tasks to complete: • Test class for DEAL_IsParentAccount() | MX | 23 | C&I_Display German and Global Client Programs FY20 | Doesn't specify component or if it exists | New |  |  |  | We don't know which component they are refering to and which other objects or components it affects.
Classifiy by Deloitte Private | 20 | Antonio Mora y Rosario Lopez Calderon | Completed | https://teams.de.deloitte.com/sites/Deal/Lists/User%20Stories/DispForm.aspx?ID=465&Source=https%3A%2F%2Fteams%2Ede%2Edeloitte%2Ecom%2Fsites%2FDeal%2FLists%2FUser%2520Stories%2FAllItems%2Easpx%23InplviewHash70ce21e7%2Dc6c7%2D4fcb%2D9b0d%2D69c10747ebfd%3D&ContentTypeId=0x0100B3FFFB2C5B67514A9A5256534188BC65 | About the user history "Classifiy by Deloitte Private": -A picklist was created with the indicated values -was added to the page layout "gCRM Global Ultimate Parent Layout" -this field was proved so that the field was available in reports. | MX | 23 | C&I_Display German and Global Client Programs FY20 | 3.-What is "the parent view lightning component"? 4.-Permissions and dependencies will be up to another sprint | New |  |  | Question: Criteria to identify a parent account:  A) It’s a parent account only when it has related children accounts.  B) When the account has a Parent ID but also related children accounts OR When the account has no Parent ID and also related children accounts  An account can be a parent account if it has no Parent Id and no related children accounts? | Dependency in progress
Client Category | 8 | Arquimidez | Completed |  | Status: -A picklist was created with the indicated values -was added to the page layout "gCRM Global Ultimate Parent Layout" | MX | 23 | C&I_Display German and Global Client Programs FY20 |  | New |  | The field has been created and in layout. Waiting only for component clarification |  |  | Has a depedency in an unespecified and/or unexisting component. Involves pending permissions to be completed
Create Account_Setup Account Team | 4 | Barbora |  |  |  | CZ |  |  |  | Done
Data Management_Create Account_concern data | 10 | Barbora |  |  |  | CZ | 30 | Data Management_Create Account_GUP | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
Data Management_Create Account_GUP | 4 | Barbora |  |  |  | CZ |  |  |  | Done
Data Management_Set qualified account to unqualified account | 20 | Barbora |  |  |  | CZ | 4 | 5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | Option 1 for design. What does deactivating billing recipient mean? To be discussed with PO. | Requires Clarification
Global Search_Account | 0 | Barbora |  |  |  | CZ |  |  |  | Done
Global Search_Contact | 0 | Barbora |  |  |  | CZ |  |  |  | Done
Global Search_External Person | 1 | Barbora |  |  |  | CZ |  |  | The shortest option from the two was implemented | Done
Highlight Panel_1 | 1 | Barbora |  |  |  | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | Waiting for dependent class to be completed | New
Highlight Panel_2 | 1 | Barbora |  |  |  | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact | Waiting for dependent class to be completed | New
Highlight Panel_3 | 1 | Barbora |  |  |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New
Mobile External Person | 2 | Barbora |  |  |  | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | Done
Mobile_Account | 2 | Barbora |  |  |  | CZ |  |  |  | Done
Mobile_Contact | 2 | Barbora |  |  |  | CZ |  |  |  | Done
Create Contact_Setup contact Team | 20 | Barbora |  |  |  | CZ |  |  |  | Done
Data Management_Contact_Deletion Requirement External Person (DSGVO) | 30 | Sabina |  |  |  | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact | New record type for "locked" layout to be created - record should be updated with this record type when the deletion request checkbox is checked. | New