## User Stories
Title | Hours | Developer | Team | Dep. Row | Dependency | Clarification/Comments | Status
5.3.2.1_10_Create Account_create address | 40 | Sabina | CZ | 4 | 5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | Auto-filling the addresses from Google is not possible for custom fields. Empire Time integration out of scope for sprint 1. Misalignment between user story and fields list - started implementing as mentioned in the user story. | In Progress
5.3.2.3_1 Create Account_Define sector and industry | 30 | Jan | CZ | 29 | Data Management_Create Account_concern data | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification | Started by Jan, but eventually blocked by data model misalignment
5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | 40 |  | MX | 16 | 5.3.2.1_6 Create Account_New Account |  | New
5.3.3.1_1 Create Contact_Enter available data_Contact | 20 | Jan | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | In Progress
5.3.3.1_4 Create Contact_Enter available data_Externe Person | 4 | Jan | CZ | 16 | 5.3.2.1_6 Create Account_New Account | Email sent out on 27/9 for small clarification. To be discussed with PO | Requires Clarification
5.3.3.2_1 Create Contact_System check, if data is existing (duplicate check) | 4 | Barbora | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact |  | In Progress
5.3.3.5 Create contact_connect a contact person to a biling address | 20 | Sabina | CZ | 2 | 5.3.2.1_10_Create Account_create address | There is a lot of text in German in the acceptance criteria. To be discussed with PO | Requires Clarification
5.3.4.1_2_Maintain Account Data -Define Sector and Industry | 40 | Jan | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
5.3.4.1_3 Maintain Account_Set Sector/Industry declination | 20 | Jan | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
5.3.4.8_1 Maintain Account Data_Notify about changes within German and Global Client Programs | 8 |  | MX |  |  |  | New
5.3.5.0_1 Maintain Contact Data_Maintaining the external person data (optional) | 2 | Barbora | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New |  |  | All | Done | In progress
5.3.7.7_1 Data Cleansing_Duplicates check (Contact) | 4 | Barbora | CZ |  |  |  | Done |  | Totals | 502 | 68 | 66
C&I_Tools_Manage Regions | 30 |  | MX |  |  | We would appreciate a mockup | New |  | CZ | 351 | 68 | 64
5.3.2.1_1 Maintain Account_Duplicate Check Edit Process | 2 |  | MX | 2 | 5.3.2.1_10_Create Account_create address |  | In Progress |  | MX | 151 | 0 | 2
5.3.2.1_6 Create Account_New Account | 4 | Jan | CZ |  |  |  | Done
5.3.2.1_6 Create Account_New Account_(mandatory) by searching in DEAL and Orbis | 35 | Sabina | CZ |  |  | We need the ORBIS managed package to proceed | On Hold
5.3.2.1_6 Create Account_New Account_Set Dunning block | 20 | Sabina | CZ |  |  |  | Done
5.3.3.2_2 Create External Person_System check, if data is existing (duplicate check) | 5 | Barbora | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New
5.3.X.X_XX Create Account_new account_generateAccountNumber | 2 | Barbora | CZ |  |  |  | Done
5.3.X.X_XX Create contact_new contact_generateContactNumber | 1 | Barbora | CZ |  |  |  | Done
5.3.X.X_XX Create external Person_new external person_generateExternalPersonNumber | 2 | Barbora | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | Done
C&I_Display German and Global Client Programs FY20 | 30 |  | MX | 29 | Data Management_Create Account_concern data |  | New
C&I_Manage FG 500 | 5 |  | MX | 23 | C&I_Display German and Global Client Programs FY20 |  | New
C&I_Manage Mountainview client portfolio | 8 |  | MX | 23 | C&I_Display German and Global Client Programs FY20 |  | New
Classifiy by Deloitte Private | 20 |  | MX | 23 | C&I_Display German and Global Client Programs FY20 |  | New
Client Category | 8 |  | MX | 23 | C&I_Display German and Global Client Programs FY20 |  | New
Create Account_Setup Account Team | 4 | Barbora | CZ |  |  |  | Done
Data Management_Create Account_concern data | 10 | Barbora | CZ | 30 | Data Management_Create Account_GUP | SIC Code - Misalignment between user story, data model, and fields list. | Requires Clarification
Data Management_Create Account_GUP | 4 | Barbora | CZ |  |  |  | Done
Data Management_Set qualified account to unqualified account | 20 | Barbora | CZ | 4 | 5.3.2.4_1 Create Account_Enter additional information on account qualifiziert | Option 1 for design. What does deactivating billing recipient mean? To be discussed with PO. | Requires Clarification
Global Search_Account | 0 | Barbora | CZ |  |  |  | Done
Global Search_Contact | 0 | Barbora | CZ |  |  |  | Done
Global Search_External Person | 1 | Barbora | CZ |  |  | The shortest option from the two was implemented | Done
Highlight Panel_1 | 1 | Barbora | CZ | 3 | 5.3.2.3_1 Create Account_Define sector and industry | Waiting for dependent class to be completed | New
Highlight Panel_2 | 1 | Barbora | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact | Waiting for dependent class to be completed | New
Highlight Panel_3 | 1 | Barbora | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person | Waiting for dependent class to be completed | New
Mobile External Person | 2 | Barbora | CZ | 6 | 5.3.3.1_4 Create Contact_Enter available data_Externe Person |  | Done
Mobile_Account | 2 | Barbora | CZ |  |  |  | Done
Mobile_Contact | 2 | Barbora | CZ |  |  |  | Done
Create Contact_Setup contact Team | 20 | Barbora | CZ |  |  |  | Done
Data Management_Contact_Deletion Requirement External Person (DSGVO) | 30 | Sabina | CZ | 5 | 5.3.3.1_1 Create Contact_Enter available data_Contact | New record type for "locked" layout to be created - record should be updated with this record type when the deletion request checkbox is checked. | New